PROJECT PROGRESS REPORT

Project Name: ACMAD Website Modernization, Product Migration and Digital Services Integration

Instructions: This form is used by Experts to report the status of progress in the project activities at the end of every month. It must be submitted to the Project Coordinator or Team Leader / Supervisor not later than the 10th of the following month.

| Reporting Expert Name | Yusuf Habu YUSUF | Project Executive | Dr Ousmane NDIAYE |
| --- | --- | --- | --- |
| Reporting Period | 25 September - 27 October | Project Coordinator | Dr. Pierre H. KAMSU TAMO |
| Year | 2026 | Action Supervisor | Ali ABANI AHMAD |
| Signature |  | Approval By (Sign) |  |
| Submission Date | 27 October 2026 | Approval Date |  |

Background and project objectives

The project continued the modernization of ACMAD public digital services on the ClimWeb and Wagtail platform. From 25 September to 27 October, production work stabilized the Regional Climate Centre website, delivered an Africa-focused ENSO information experience, expanded public editorial controls and established a substantially broader staff workspace. Development and feature branches then added GIS-linked products, multilingual publications, richer institutional timelines, CUIP and Summer School improvements, and the new CLIMSA website.

Objectives for the period were to: (1) complete RCC operational and hosting improvements; (2) publish clearer ENSO information and related content; (3) strengthen homepage, product and institutional content management; (4) implement secure staff reporting, HR and Google Drive workflows; (5) advance CLIMSA, Summer School and news-media delivery; and (6) prepare branch consolidation, validation, deployment and handover.

Achievements

The table below maps verified work across production, develop and active feature branches. "Implemented" means the capability exists in the codebase; release completeness depends on the code line identified in the realization indicator and on final migration, regression, deployment and editorial validation.

| Planned activities / tasks (per the contract Terms of Reference | Status of deliverables at the end of the period |  |  |  | Comments / justification |
| --- | --- | --- | --- | --- | --- |
|  | Deliverable (contract reference) | Status | Milestones completed | Realization indicator |  |
| RCC stabilization and operational controls | Stable RCC services, hosting and managed data-import operations. | Completed | Restored missing page titles, expanded training and coordination content, configured RCC subdomain hosting, exposed import-stop actions, clarified active-run behavior and restored compact dataset selectors. | Production branch; commits 291e081c, 591019c7, a06f1fac, d02c9040, 5deb5278 and e9297323. | Merged to production. |
| Africa-focused ENSO information hub | Dedicated ENSO page with bulletins, explanations and related content. | Implemented | Created the Africa-focused El Nino page, broadened it to ENSO, moved the latest bulletin into the hero, added related news, events and partner activities, and improved mobile pagination and imagery. | Production branch; ENSO delivery from cefe3dd7 through d2e3b50d with follow-up fixes. | Merged to production. |
| Homepage and editorial controls | Maintainable hero, featured-content and public-page controls. | Implemented | Made the hero carousel configurable, added featured products and upcoming events, expanded homepage controls, refined Media Center video presentation and improved organisation, service and product-page administration. | Production branch; hero-carousel, ui-fixes and develop merge history. | Core work merged; later refinements remain on develop. |
| Security and platform reliability | Safer public forms, authentication routes and schema evolution. | Completed | Hardened product subscriptions, disabled unnecessary public authentication pages, reconciled conflicting migrations and repaired About and ENSO test failures. | Production branch; a89d73b9, 68058d29, 2f2aca02 and 2910d4d0. | Merged to production. |
| Staff dashboard and report workflow | Staff assignments, proposals, reports, review and approval in one workspace. | Implemented | Built staff dashboards and training assignments, improved report submission and approval, supported multiple report documents and added bulk profile invitations. | Production branch; 68802d0c, 3dbb5719, a70a50c4 and 4b2b09fe. | Merged to production. |
| HR notifications and Google Drive integration | Traceable HR activities, workflow notifications and managed staff files. | Implemented | Added workflow email notifications and delivery tracking, enhanced HR activity management, integrated Google Drive browsing and file movement, and synchronized report documents with operational checks. | Production branch; 12b9c89c, 5a6ae2cc, f6520e2d and bfc35fdc. | Merged to production; live credentials still require environment validation. |
| Institutional profiles and presentation | Dedicated leadership content and consistent portrait presentation. | Implemented | Added a Director General profile page, improved institutional and staff portrait framing, expanded directories and preserved responsive presentation. | Production and develop branches; 76b9ff45, 932b2025, 6e6ebf8f and 71392ded. | Production baseline plus a later develop refinement. |
| Products, publications, timeline and CUIP | Expanded product links and richer institutional and service content. | Implemented on develop | Added editor-managed GIS applications, multilingual publication metadata, supporting timeline documents, CUIP rationale content and stronger Summer School joining actions and galleries. | Develop branch; b787d50c, a43bbdbc, c6a2b830, 57df172e and 80bf1ae7. | Awaiting promotion to production. |
| CLIMSA website customization | Dedicated CLIMSA application, homepage, About page and programme interface. | Implemented on feature branch | Built CLIMSA models, editable content, responsive styling, subdomain configuration, tests and deployment documentation; added the About page and refined programme and partner presentation. | climsa-website and codex/climsa-website-clean branches through 22 October. | Select one canonical branch and complete integrated validation. |
| Summer School and news-media expansion | Daily activities, reviews and richer editorial media blocks. | Implemented on feature branch | Added Summer School daily activities and reviews, gallery and navigation refinements, plus news body videos, gallery videos, quotation content, mosaic rendering and expanded tests. | summer-school-enhancement branch through a79f82e7. | Awaiting integration with develop and production. |
| Release integration and handover readiness | Consolidated, tested and deployable release across active code lines. | In progress | Documented staff operations and deployment behavior, identified duplicate CLIMSA histories, separated production, develop and feature-branch scope, and prepared the remaining validation sequence. | ui-fixes, develop, CLIMSA and Summer School branches; current workspace reviewed 27 October. | Branch consolidation, regression QA, deployment validation and acceptance remain. |

Planning for the next month

| Roadmap deliverable | Milestone / target date | Planned activities | Expected verification indicator |
| --- | --- | --- | --- |
| Consolidate the CLIMSA and Summer School code lines | 28-30 October 2026 | Select the canonical CLIMSA history and definitive Summer School/news branch, then prepare a conflict-controlled integration branch. | One reviewed integration branch with duplicate histories removed from the merge plan. |
| Promote validated develop work | 30 October-3 November 2026 | Review GIS, publications, timeline, CUIP and Summer School changes; apply migration checks and merge the approved develop delta. | Approved release candidate containing the seven post-production develop changes. |
| Integrated regression and migration quality assurance | 3-7 November 2026 | Run CLIMSA, Summer School, news, RCC navigation, staff, product and deployment test suites together and resolve shared-schema conflicts. | Passing integrated tests, clean migration graph and documented known issues. |
| Production routing and deployment validation | 9-13 November 2026 | Validate subdomain routing, static assets, seeded content, environment configuration and production startup for ACMAD, RCC and CLIMSA. | Deployment checklist completed with verified domains, assets and administrative access. |
| Editor and administrator handover | 16-20 November 2026 | Update staff-workspace, CLIMSA, Summer School media and public-content guidance; conduct acceptance review and record ownership. | Approved editor/admin guide, acceptance record and assigned operational owners. |

Annexes and evidence register

| Reference | Evidence / deliverable | Location or identifier |
| --- | --- | --- |
| A1 | RCC stabilization, services, hosting and managed import controls | https://github.com/ACMAD-Niamey/climweb/tree/production |
| A2 | Africa-focused ENSO page, bulletins and related content | https://github.com/ACMAD-Niamey/climweb/tree/el-nino-africa |
| A3 | Staff workspace, HR workflows, notifications and Google Drive integration | https://github.com/ACMAD-Niamey/climweb/tree/staff-dashboard-enhancements |
| A4 | Homepage, organisation, products, publications, timeline and CUIP improvements | https://github.com/ACMAD-Niamey/climweb/tree/ui-fixes |
| A5 | Post-production GIS, publications, timeline and service additions | https://github.com/ACMAD-Niamey/climweb/tree/develop |
| A6 | CLIMSA website, About page, programme interface and deployment configuration | https://github.com/ACMAD-Niamey/climweb/tree/climsa-website |
| A7 | Summer School daily activities and reviews plus news videos, quotes and galleries | https://github.com/ACMAD-Niamey/climweb/tree/summer-school-enhancement |

Permanent link to access your reports and to navigate to the exact link with your current deliverables / evidence: